[image: image1.wmf]




FACT SHEET





Improvements to US 181 at the Harbor Bridge - Environmental Documentation and Schematic Development              


October 2011





What is the Harbor Bridge Project?


Proposed improvements to US 181 at the Harbor Bridge over the Corpus Christi Ship Channel


Project would extend from Beach Ave on US 181 to Morgan Ave on SH 286


Federal Highway Administration is the lead Federal agency for the project


TxDOT is the joint lead agency





Project Development Phases and Anticipated Timeline


Public involvement throughout project


Feasibility Study: completed in 2003


Initiate Environmental Impact Statement (EIS) project development with two sets of public and agency scoping meetings - 2011


Develop alternatives and begin agency coordination - 2012


Public Meeting – 2012 - 2013


Prepare and review draft environmental document - 2012  - 2014


Public Meeting – Design Guideline Workshop - 2013


Public Hearing – 2014 - 2015


Prepare and review final environmental document – 2014 - 2017


Public involvement throughout process


Environmental Clearance - ROD issued 2017 or as early as 2014


Permits and approvals – 2015 - 2017


Right-of-way mapping/acquisition: 2015 – 2017


Preparation of detailed construction plan: 2015 - 2017


Start of phased construction – 2017 - 2020





Stay involved in the Harbor Bridge Project by participating in the following:


Submit comments at today’s Public Scoping Meeting and afterward via mail, email or online.


Follow the project online: www.ccharborbridgeproject.com


Sign up to be on our mailing list (tonight or on the website)


Attend public meetings and public hearing


Participate in small stakeholder meetings


Read our newsletter


Participate in the Citizens’ Advisory Committee or Technical Advisory Committee








For more information, contact:


TxDOT Project Manager, Victor E. Vourcos at: 361-808-2378


TxDOT Public Information Officer, Tom Tagliabue at  361.808.2481 





www.ccharborbridgeproject.com
















































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































For more information, contact:


TxDOT Project Manager, Victor E. Vourcos at: 361-808-2378


TxDOT Public Information Officer, Tom Tagliabue at 361-808-2481. 





� HYPERLINK "http://www.ccharborbridgeproject.com" �www.ccharborbridgeproject.com�

















Corpus Christi District





What is an Environmental Impact Statement? � 


Document required by National Environmental Policy Act for large construction projects that use federal highway funds.





Discloses project information, describes the project and study areas, and analyzes possible environmental consequences associated with construction.





Includes public involvement at beginning of EIS development and throughout the process








Must be approved by the Federal Highway Administration before right-of-way acquisition and construction can begin.


























